## Worksheet 1
|  | Duration |  |  | Resource requirements
No. | Description | α | m | β | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10
T1 | Seek financial assistance | 5 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2 | Professionally demolish existing structure | 2 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
T3 | Professionally prepare and lay new foundation | 5 | 8 | 15 | 20 | 0 | 10 | 1 | 0 | 3 | 5 | 0 | 0 | 0
T4 | Professionally build walls | 8 | 10 | 20 | 10 | 20 | 10 | 2 | 0 | 2 | 5 | 0 | 0 | 0
T5 | Professionally build roof | 8 | 10 | 20 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 10
T6 | Professionally install plumbing | 5 | 8 | 15 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
T7 | Professionally install electrical equipment | 5 | 8 | 15 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
T8 | Professionally finish interior | 8 | 10 | 20 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 4
T9 | Reoccupy structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0